Project Ordolix

Enterprise Project & Issue Tracking Platform

Jira Cloud Replacement — Complete Project Blueprint

Proofpoint — IT Engineering

Version 3.0 — February 2026

Classification: Internal / Confidential

# Table of Contents

Table of Contents	1

Executive Summary	1

Project Overview	1

Problem Statement	1

Proposed Solution	1

Project Goals	1

Success Criteria	1

Scope Definition	1

In Scope — Core Platform (v1.0)	1

In Scope — Native Add-On Replacements (v1.0)	1

In Scope — External Integrations (v1.0)	1

Out of Scope (Future Phases)	1

Development Methodology	1

Test-Driven Development (TDD)	1

TDD Rules	1

Testing Architecture	1

Claude Code Skills & Agents	1

Skill File Structure	1

Agent Mode Workflows	1

Self-Documenting Code	1

Documentation Requirements	1

Tooltip-Driven In-App Documentation	1

Tooltip Implementation	1

Coding Standards & Architecture	1

Directory Structure	1

Naming Conventions	1

Error Handling	1

Logging Strategy	1

Environment Configuration	1

CI/CD Pipeline	1

Pipeline Overview	1

GitHub Actions Workflow	1

Branch Strategy	1

Quality Gates	1

Hosting Architecture	1

Two-Track Hosting Strategy	1

Track A: Independent Development (Vercel + Neon)	1

Track A: Architecture Adaptations	1

Track B: Enterprise Production (Azure)	1

Migration Path: Track A to Track B	1

Monitoring & Observability	1

Track A Monitoring (Vercel)	1

Track B Monitoring (Azure)	1

Application-Level Monitoring (Both Tracks)	1

Technology Stack	1

Frontend	1

Backend	1

Infrastructure & Auth	1

External Integrations	1

Core Data Model	1

Core Entities	1

Add-On Feature Entities	1

Integration Entities	1

Feature Specifications	1

Feature Implementation Priority	1

Key Architecture Decisions by Feature	1

Development Plan	1

Phase 1: Foundation + Demo Prep (Months 1–3)	1

Phase 2: Platform Complete (Months 4–5)	1

Phase 3: Integrations & Enterprise Features (Months 6–7)	1

Phase 4: Launch (Month 8)	1

Demo Strategy for Stakeholder Buy-In	1

Demo Environment	1

Demo Narrative	1

Buy-In Success Criteria	1

Risks and Mitigations	1

Cost Analysis	1

Cost Comparison	1

Immediate Next Steps	1

Appendices	1

Appendix A: Add-On Feature Mapping & Cost Elimination	1

Appendix B: AQL Specification	1

Appendix C: Integration API Reference	1

Appendix D: SharePoint-Confluence Migration Mapping	1

Appendix E: Claude Code Context Files	1

# Executive Summary

Project Ordolix is an internally developed enterprise project and issue tracking platform designed to replace Ordolixsian Jira Cloud, Confluence (via SharePoint integration), and all associated marketplace add-ons across the organization. This initiative is driven by significant and ongoing cost increases from Ordolixsian — spanning base licensing, Confluence, and the extensive marketplace add-ons (Tempo, ScriptRunner, BigPicture, eazyBI, Insight, ProForma, and others) required for essential functionality.

The platform will be built using Next.js, PostgreSQL (Neon), and Redis (Upstash), deployed on Vercel for independent development and stakeholder demos, with a defined migration path to Azure infrastructure once organizational buy-in is secured. Development will be driven primarily by Claude Code in agent mode, following a test-driven development (TDD) methodology with self-documenting code, Claude Code skills files for repeatable patterns, and tooltip-driven in-app documentation.

This document serves as the complete project blueprint — designed to be consumed directly by Claude Code as the primary context file, enabling autonomous development with minimal human intervention. Every architectural decision, coding standard, naming convention, and feature specification is captured here so that Claude Code can begin building immediately upon project initialization.

# Project Overview

## Problem Statement

Ordolixsian has implemented substantial price increases for Jira Cloud, creating an unsustainable cost trajectory. Beyond base licensing, the organization pays significant additional fees for marketplace add-ons required for essential functionality: ScriptRunner for custom automation, Tempo for time tracking, BigPicture for Gantt charts, Epic Sum Up for field aggregation, eazyBI for reporting, ProForma for forms, Insight for asset management, and others. These add-on costs often exceed the base licensing itself. The Jira-Confluence coupling limits SharePoint adoption, and integration friction with the Microsoft 365 ecosystem compounds operational challenges.

## Proposed Solution

Build a custom project management and issue tracking platform that mirrors actively used features while building all commonly purchased add-on functionality directly into the core platform. The solution will be developed independently first using existing Vercel and Neon infrastructure to prove viability, then migrated to enterprise Azure infrastructure once organizational buy-in is secured.

## Project Goals

- Eliminate Jira Cloud, Confluence, and all marketplace add-on licensing costs

- Build all commonly purchased add-on functionality natively (time tracking, Gantt charts, scripting, advanced SLAs, test management, forms, reporting, CMDB, approvals, retrospectives)

- Achieve feature parity with current organizational usage within 8 months

- Integrate with SharePoint (Confluence replacement), GitHub, Salesforce, Power BI, and MCP

- Provide seamless SSO integration with Azure AD / Entra ID

- Enable full data migration from Jira with zero data loss, including all add-on data

- Develop independently first on Vercel/Neon to prove viability before requesting enterprise infrastructure

- Create a self-documenting, test-driven codebase that Claude Code can develop autonomously

## Success Criteria

- Working prototype on Vercel with core features demonstrable to stakeholders within 3 months

- All marketplace add-on functionality replaced by native features

- All active projects migrated from Jira with complete data integrity

- User adoption rate exceeding 90% within 30 days of production launch

- Page load times under 500ms for primary views

- 100% test coverage on core business logic (workflows, SLAs, rollups, permissions)

- All external integrations operational at launch

# Scope Definition

## In Scope — Core Platform (v1.0)

- Project management: projects, issue types, subtasks, epics, labels, components, versions

- Configurable workflow engine with custom states, transitions, validators, post-functions, and approval gates

- Board views: Kanban, list view, and backlog management with real-time updates

- Custom fields: text, number, select, multi-select, date, user picker, cascading select with rollup support

- Role-based permission schemes with project-level and global-level controls

- Full-text search with Ordolix Query Language (AQL)

- Comments, @mentions, attachments, activity history, and checklists

- Automation engine: triggers, conditions, actions, and scheduled rules

- Dashboard system with configurable widgets and saved filters

- Notification system: in-app, email digest, and webhook-based

- SSO/SAML integration with Azure AD / Microsoft Entra ID

- REST API with OpenAPI documentation

- Jira data migration tooling including all add-on data

- Audit logging for compliance and security

- Service management: request types, queues, SLA tracking, customer portal

## In Scope — Native Add-On Replacements (v1.0)

- Epic Sum Up: native field rollup/aggregation from child to parent issues

- Gantt Charts: interactive timeline with dependencies, critical path, resource view, baseline comparison

- Advanced SLAs: multi-metric, business calendars, escalation chains, breach predictions

- Time Tracking: timers, manual entry, timesheets, approvals, billable categorization, budget tracking

- MCP Server: Model Context Protocol for AI assistant interaction

- ScriptRunner: sandboxed TypeScript scripting engine with Ordolix SDK

- Checklists: assignable items, templates, workflow-integrated completion requirements

- Assets/CMDB: configurable asset types, relationships, issue linking, import/sync

- Incident Management: severity escalation, communication templates, status page

- Test Management: test cases, plans, runs, traceability, defect linking

- Approval Workflows: multi-stage, parallel/sequential, Azure AD groups, delegation

- Report Builder: drag-and-drop dimensions/measures, chart types, scheduled delivery

- Dynamic Forms: conditional logic, multi-page, validation, form-to-issue mapping

- Retrospective Boards: anonymous mode, voting, auto-create issues from action items

## In Scope — External Integrations (v1.0)

- SharePoint: bi-directional linking, search, embedded content, page creation (Confluence replacement)

- GitHub: PR/branch/commit linking, automated transitions, deployment tracking

- Salesforce: case-to-ticket creation, field mapping, bi-directional status sync

- Power BI: OData feed, dataset schemas, .pbit templates, row-level security

## Out of Scope (Future Phases)

- Native mobile applications (responsive web in v1)

- Plugin/marketplace ecosystem

- Embedded Power BI visuals within Ordolix

- Salesforce CPQ/billing integration

- GitHub Actions triggering from Ordolix

- Multi-tenant SaaS deployment

- AI-powered features beyond MCP (predictive assignment, smart categorization)

# Development Methodology

## Test-Driven Development (TDD)

All feature development follows a strict TDD cycle: write failing tests first, implement the minimum code to pass, then refactor. This is non-negotiable and applies to every module. Claude Code should always generate test files before implementation files.

### TDD Rules

- Every feature branch must include tests written before implementation code

- No PR is mergeable without passing tests and minimum coverage thresholds

- Unit tests (Vitest): all business logic, utilities, validators, rollup calculations, SLA computations, AQL parser

- Integration tests (Vitest + Prisma): database operations, API routes, workflow transitions, permission checks, automation rule execution

- End-to-end tests (Playwright): critical user flows including board interactions, Gantt drag-and-drop, form submission, timesheet approval

- Test coverage targets: 100% on core business logic (workflow engine, SLA calculations, rollup engine, permission checks), 80% overall

- Snapshot tests for UI components to catch unintended visual regressions

### Testing Architecture

- Test file co-location: tests live adjacent to source files (e.g., workflow-engine.ts and workflow-engine.test.ts in the same directory)

- Factory pattern: use factory functions (e.g., createTestIssue(), createTestWorkflow()) to generate test fixtures with sensible defaults and overrides

- Database test isolation: each integration test suite gets a fresh Neon branch or transaction rollback to ensure test independence

- External API mocking: use MSW (Mock Service Worker) for SharePoint Graph API, GitHub API, and Salesforce API mocks with realistic response fixtures

- Performance benchmarks: Vitest bench for critical paths (AQL parsing, rollup computation, SLA calculation) with regression alerts

## Claude Code Skills & Agents

Claude Code skills files define repeatable patterns and conventions that ensure consistency across the codebase. These are stored in the repository and loaded by Claude Code to maintain architectural coherence across development sessions.

### Skill File Structure

- skills/feature-module.md — Pattern for creating a new feature module: directory structure, file naming, required exports, test structure, and Prisma model conventions

- skills/api-endpoint.md — Pattern for tRPC router procedures: input validation (Zod), authorization checks, error handling, audit logging, and response formatting

- skills/ui-component.md — Pattern for React components: props interface, JSDoc documentation, Tailwind styling conventions, tooltip integration, accessibility requirements

- skills/integration-connector.md — Pattern for external integrations: OAuth flow, API client structure, webhook handler, error retry, mock fixtures

- skills/database-migration.md — Pattern for schema changes: Prisma model updates, migration generation, seed data updates, rollback procedure

- skills/test-suite.md — Pattern for test files: factory usage, assertion style, mock setup, cleanup, coverage requirements

### Agent Mode Workflows

Claude Code agent mode enables multi-step autonomous development. The following agent workflows are defined for common development tasks:

- New Feature Agent: reads feature spec from this document → creates Prisma model → generates migration → writes tests → implements tRPC router → builds UI components → adds tooltips → runs tests → commits

- Bug Fix Agent: reproduces issue with failing test → implements fix → verifies test passes → checks for regressions → commits

- Integration Agent: reads integration spec → creates API client → builds webhook handler → writes mock fixtures → implements tests → builds UI → commits

- Refactor Agent: identifies code smells → writes characterization tests → refactors → verifies tests still pass → updates documentation → commits

## Self-Documenting Code

The codebase must be comprehensible without external documentation. Every export, function, type, and component is documented inline.

### Documentation Requirements

- JSDoc/TSDoc on all exported functions, types, interfaces, and components with @description, @param, @returns, @throws, and @example tags

- Module-level documentation: every file starts with a JSDoc comment explaining the module’s purpose, responsibilities, and key dependencies

- Inline comments for non-obvious business logic (SLA calculations, rollup algorithms, permission resolution, AQL parsing)

- README.md per feature directory explaining the module architecture, key decisions, and usage examples

- Type-driven documentation: prefer self-describing type names and union types over comments (e.g., type SLAStatus = "active" | "paused" | "breached" | "completed")

- Auto-generated API documentation: OpenAPI spec generated from tRPC router definitions using trpc-openapi, served at /api/docs

- Database documentation: Prisma schema comments on all models and fields, auto-generated ERD diagram updated on schema changes

## Tooltip-Driven In-App Documentation

Every feature, field, button, and configuration option in the UI includes contextual tooltip documentation that explains what it does, why it exists, and how to use it. This eliminates the need for separate user guides and makes the application self-teaching.

### Tooltip Implementation

- Tooltip component: a reusable <HelpTooltip> component that renders a (?) icon with hover/click tooltip content

- Tooltip content source: tooltips are stored as a structured JSON/TypeScript dictionary (tooltips.ts) organized by feature module, enabling bulk updates and translation

- Rich tooltips: support for formatted text, links to related features, and short animated GIFs for complex interactions (Gantt drag-and-drop, workflow builder)

- Contextual placement: tooltips appear on field labels in issue views, column headers in boards, configuration options in admin panels, and action buttons

- First-use guides: on first interaction with a feature, show an expanded tooltip walkthrough that can be dismissed permanently

- Admin-configurable: administrators can edit tooltip content from the Ordolix admin panel without code changes

- Search integration: tooltip content is indexed and searchable from a global help search (Cmd+/)

# Coding Standards & Architecture

## Directory Structure

The project uses a feature-based modular structure. Each feature module is self-contained with its own routes, components, logic, tests, and types. This structure enables Claude Code to work on individual modules without full codebase context.

- src/app/ — Next.js App Router pages and layouts

- src/modules/ — Feature modules (issues/, workflows/, boards/, time-tracking/, gantt/, sla/, test-management/, assets/, scripts/, forms/, reports/, incidents/, retrospectives/, approvals/, checklists/)

- src/modules/[module]/components/ — React components specific to the module

- src/modules/[module]/server/ — tRPC routers, business logic, and database operations

- src/modules/[module]/types/ — TypeScript types and Zod schemas

- src/modules/[module]/tests/ — Unit and integration tests

- src/modules/[module]/tooltips.ts — Tooltip content dictionary for the module

- src/modules/[module]/README.md — Module documentation

- src/shared/ — Shared components, hooks, utilities, and types used across modules

- src/integrations/ — External integration modules (sharepoint/, github/, salesforce/, powerbi/, mcp/)

- src/server/ — Server configuration, middleware, auth, and database client

- prisma/ — Prisma schema, migrations, and seed files

- skills/ — Claude Code skill files for development patterns

- tests/e2e/ — Playwright end-to-end test suites

- tests/fixtures/ — Shared test factories and mock data

## Naming Conventions

| Category | Convention | Example |
| --- | --- | --- |
| Files (components) | PascalCase.tsx | IssueDetail.tsx, GanttChart.tsx |
| Files (logic) | kebab-case.ts | workflow-engine.ts, sla-calculator.ts |
| Files (tests) | *.test.ts / *.spec.ts | workflow-engine.test.ts |
| React components | PascalCase | IssueCard, BoardColumn, GanttTimeline |
| Functions/hooks | camelCase | useIssueQuery, calculateRollup, parseAQL |
| Types/interfaces | PascalCase | Issue, WorkflowTransition, SLAConfig |
| Prisma models | PascalCase singular | Issue, TimeLog, TestCase, Asset |
| Database tables | Auto from Prisma (snake_case) | time_log, test_case, asset |
| tRPC routers | camelCase | issueRouter, workflowRouter, timeTrackingRouter |
| API routes | kebab-case | /api/issues, /api/time-tracking, /api/gantt-dependencies |
| Environment variables | UPPER_SNAKE_CASE | DATABASE_URL, AZURE_AD_CLIENT_ID |
| CSS/Tailwind | Utility classes only | No custom CSS files; Tailwind utilities |
| AQL keywords | UPPER_CASE | AND, OR, ORDER BY, IS EMPTY, CONTAINS |

## Error Handling

- Typed error classes: AppError base class with subclasses (ValidationError, NotFoundError, PermissionError, ConflictError, IntegrationError, ScriptExecutionError)

- Error codes: every error has a machine-readable code (e.g., WORKFLOW_TRANSITION_BLOCKED, SLA_CONFIG_INVALID, SCRIPT_TIMEOUT) for client-side handling

- Centralized error boundary: React ErrorBoundary at the app level and per-module level with graceful fallback UI

- API error responses: consistent JSON structure with { code, message, details, requestId } on all error responses

- Integration error handling: external API failures (SharePoint, GitHub, Salesforce) are caught, logged, and surfaced to users with retry options — never silently swallowed

- Audit trail on errors: all errors are logged with correlation IDs, user context, and stack traces to the structured logging system

## Logging Strategy

- Structured JSON logging via Pino (lightweight, fast, JSON-native)

- Log levels: error (failures), warn (degraded states), info (business events), debug (development detail)

- Correlation IDs: every incoming request gets a unique requestId propagated through all log entries and API responses

- Business event logging: all workflow transitions, automation executions, script runs, SLA events, and permission checks logged as structured info events

- No sensitive data in logs: PII, tokens, and credentials are redacted automatically via Pino redaction config

- Log shipping: stdout to Vercel Logs (Track A) or Azure Monitor / Application Insights (Track B)

## Environment Configuration

- All configuration via environment variables, validated on startup with Zod (env.ts) — app crashes immediately with clear error if required vars are missing

- Environment tiers: local (.env.local), preview (Vercel preview deployments), production (Vercel production or Azure)

- Secrets management: Vercel Environment Variables for Track A, Azure Key Vault for Track B

- Feature flags: environment-variable-based feature flags for progressive rollout of add-on features (e.g., FEATURE_GANTT_ENABLED=true)

- Config validation runs in CI: GitHub Actions validates that all required env vars are documented and typed

# CI/CD Pipeline

## Pipeline Overview

The CI/CD pipeline uses GitHub Actions for testing and quality gates, with Vercel handling deployment. Every push triggers the pipeline, and no code reaches production without passing all gates.

## GitHub Actions Workflow

| Stage | Trigger | Actions | Failure Behavior |
| --- | --- | --- | --- |
| Lint | Every push / PR | ESLint + Prettier check on all changed files | Block merge |
| Type Check | Every push / PR | tsc --noEmit across entire codebase | Block merge |
| Unit Tests | Every push / PR | Vitest run with coverage report | Block merge if coverage drops below threshold |
| Integration Tests | Every push / PR | Vitest with Neon branch database | Block merge |
| E2E Tests | PR to main only | Playwright against Vercel preview deployment | Block merge |
| Security Scan | Every push / PR | npm audit + CodeQL analysis + dependency check | Block merge on critical/high |
| Schema Validation | When prisma/ changes | Prisma validate + migration dry run against Neon branch | Block merge |
| Build | Every push / PR | next build to verify production build succeeds | Block merge |
| Deploy Preview | Every PR | Vercel preview deployment with unique URL | Informational only |
| Deploy Production | Merge to main | Vercel production deployment | Auto-rollback on health check failure |

## Branch Strategy

- main — production branch, always deployable, protected with required reviews and CI pass

- feature/* — feature branches from main, one per feature module or user story

- fix/* — bug fix branches

- Squash merge to main to keep history clean

- Neon database branching: each PR gets an isolated Neon database branch for integration testing, auto-deleted on PR close

- Vercel preview deployments: each PR gets a unique preview URL for stakeholder review and E2E testing

## Quality Gates

- All tests pass (unit, integration, E2E)

- Test coverage does not decrease (enforced by coverage diff in CI)

- No ESLint errors or warnings

- No TypeScript errors

- No critical or high security vulnerabilities in dependencies

- Prisma schema validates and migrations generate cleanly

- Bundle size does not increase by more than 5% without justification

- All new exported functions/types have JSDoc documentation

# Hosting Architecture

## Two-Track Hosting Strategy

The project follows a two-track hosting strategy. Track A enables independent development and stakeholder demos at minimal cost using existing infrastructure. Track B defines the enterprise production environment activated once organizational buy-in is secured. The application code is identical across both tracks — only infrastructure configuration differs.

## Track A: Independent Development (Vercel + Neon)

This track uses existing Vercel and Neon accounts (shared with Underpriced AI infrastructure) to develop, test, and demonstrate Ordolix at near-zero incremental cost.

| Service | Purpose | Tier / Cost | Notes |
| --- | --- | --- | --- |
| Vercel | Next.js hosting, preview deployments, edge functions, CI/CD | Pro ($20/mo, existing) | Handles deployment, SSL, CDN, and preview URLs for stakeholder demos |
| Neon | PostgreSQL database with branching | Pro (existing) | Database branching for PR isolation; connection pooling via Neon’s serverless driver |
| Upstash | Serverless Redis for caching, pub/sub, rate limiting | Free tier → Pay-as-you-go | Vercel integration available; replaces self-hosted Redis |
| Upstash QStash | Message queue and scheduled jobs (BullMQ replacement) | Free tier (500 msgs/day) | HTTP-based message queue for automation execution, SLA timers, scheduled reports |
| Trigger.dev | Background job execution (alternative/complement to QStash) | Free tier → Hobby | For long-running jobs: migration scripts, bulk operations, report generation |
| Cloudflare R2 | Object storage for attachments (S3-compatible) | Free tier (10GB) | Zero egress fees; S3-compatible API so MinIO code works unchanged |
| Ably or Pusher | Managed real-time messaging (WebSocket alternative) | Free tier → Pay-as-you-go | Replaces Socket.io; works with Vercel serverless. Alternatively use SSE + Upstash pub/sub |
| GitHub | Source control, CI/CD via Actions, code review | Free (private repos) | 2,000 CI/CD minutes/month on free tier |
| Azure AD Dev Tenant | SSO authentication for development | Free (M365 Developer Program) | Full Azure AD SSO without Proofpoint production tenant access |

Estimated monthly cost for Track A: $20–40 (leveraging existing Vercel/Neon subscriptions and free tiers). This is the cost presented to stakeholders alongside the current Ordolixsian spend for maximum contrast.

### Track A: Architecture Adaptations

Running on Vercel’s serverless platform requires specific architectural choices that differ from a traditional server deployment:

- Serverless-first: all API routes are stateless serverless functions; no long-running processes

- Real-time: use Ably/Pusher managed service or SSE (Server-Sent Events) with Upstash Redis pub/sub instead of raw WebSocket connections. The real-time module is abstracted behind a RealTimeProvider interface so the implementation can swap between managed service (Track A) and raw WebSocket (Track B) without changing consumer code

- Background jobs: Upstash QStash for message queuing and scheduled tasks (replaces BullMQ). Jobs are triggered via HTTP webhooks to Vercel API routes. For jobs exceeding Vercel’s 60-second function timeout, use Trigger.dev

- Database connections: use Neon’s serverless driver (@neondatabase/serverless) with connection pooling for efficient serverless database access

- File storage: Cloudflare R2 via S3-compatible SDK. The storage module is abstracted behind a StorageProvider interface (R2 for Track A, Azure Blob for Track B)

- Cron jobs: Vercel Cron (vercel.json crons config) triggers API routes on schedule for SLA calculations, report generation, and data aggregation

## Track B: Enterprise Production (Azure)

Once organizational buy-in is secured, the application migrates to Azure infrastructure for enterprise-grade reliability, security, and compliance.

| Service | Purpose | Tier | Notes |
| --- | --- | --- | --- |
| Azure Container Apps (or AKS) | Application hosting | Production | Managed containers with auto-scaling; AKS if Kubernetes expertise available |
| Azure Database for PostgreSQL | Managed PostgreSQL | Flexible Server | Migrate from Neon via pg_dump/pg_restore; same Prisma schema |
| Azure Cache for Redis | Managed Redis | Standard | Direct replacement for Upstash; BullMQ replaces QStash |
| Azure Blob Storage | Object storage | Hot tier | S3-compatible API; StorageProvider interface swaps transparently |
| Azure Key Vault | Secrets management | Standard | Replaces Vercel Environment Variables for sensitive config |
| Azure Monitor + App Insights | Monitoring and observability | Standard | Structured logging, metrics, distributed tracing, alerts |
| Azure Front Door / CDN | CDN and edge caching | Standard | Global content delivery and DDoS protection |
| Azure AD / Entra ID | Enterprise SSO | Production tenant | Switch from dev tenant to Proofpoint production Azure AD |

### Migration Path: Track A to Track B

The migration from Vercel/Neon to Azure is designed to be straightforward because all infrastructure-dependent code is abstracted behind provider interfaces:

- Database: pg_dump from Neon, pg_restore to Azure PostgreSQL. Prisma schema and migrations are identical. Update DATABASE_URL environment variable.

- Redis: switch from Upstash SDK to ioredis connecting to Azure Cache for Redis. Update REDIS_URL. If using BullMQ on Azure, replace QStash webhook handlers with BullMQ worker processes.

- Storage: change StorageProvider from R2Adapter to AzureBlobAdapter. Update storage credentials. Migrate existing files via rclone or azcopy.

- Real-time: swap from Ably/Pusher adapter to native WebSocket adapter (Socket.io on Azure Container Apps supports persistent connections). RealTimeProvider interface unchanged.

- Auth: swap Azure AD dev tenant credentials for Proofpoint production tenant credentials. No code changes.

- Deployment: replace Vercel deployment with Azure Container Apps deployment via GitHub Actions. Dockerfile already exists for local development.

- DNS: point Ordolix.proofpoint.com to Azure Front Door instead of Vercel.

# Monitoring & Observability

## Track A Monitoring (Vercel)

- Vercel Analytics: page load times, Web Vitals (LCP, FID, CLS), and serverless function duration

- Vercel Logs: real-time structured log viewing for all serverless function executions

- Upstash Console: Redis metrics (commands/sec, memory, latency) and QStash job monitoring

- Neon Dashboard: database metrics (connections, query latency, storage) and branch management

- Sentry (free tier): error tracking with source maps, breadcrumbs, and release tracking

- GitHub Actions: CI/CD pipeline metrics (build times, failure rates, test durations)

## Track B Monitoring (Azure)

- Azure Application Insights: distributed tracing, dependency tracking, live metrics stream, and custom telemetry

- Azure Monitor: infrastructure metrics, log analytics, alert rules, and dashboards

- Custom health endpoints: /api/health returns status of all dependencies (database, Redis, external APIs) for load balancer health checks

- SLA monitoring dashboard: internal dashboard tracking Ordolix’s own uptime and performance SLAs

- Alerting: PagerDuty or Teams integration for critical alerts (database connection failures, SLA processing delays, integration auth failures)

## Application-Level Monitoring (Both Tracks)

- Request correlation: every request gets a unique ID propagated through logs, API responses, and background jobs

- Business metrics: track automation execution rates, SLA compliance, script execution times, and integration sync status

- Performance budgets: alert when API response times exceed 200ms (p95) or page loads exceed 500ms

- Error rate monitoring: alert when error rate exceeds 1% of requests in a 5-minute window

- Background job monitoring: track QStash/BullMQ job success rates, queue depths, and processing latency

# Technology Stack

## Frontend

| Technology | Rationale |
| --- | --- |
| Next.js 15 (App Router) | Full-stack React framework deployed on Vercel. Existing team expertise from Underpriced AI. |
| TypeScript (strict mode) | Type safety across the entire codebase. strict: true, noUncheckedIndexedAccess: true in tsconfig. |
| Tailwind CSS | Utility-first CSS. No custom CSS files. All styling via Tailwind utilities. |
| shadcn/ui | Accessible component library built on Radix UI. Fully customizable, copy-paste model. |
| React Query (TanStack) | Server state with caching, optimistic updates, and background refetching. |
| D3.js | Gantt chart rendering, dependency diagrams, and custom data visualizations. |
| Monaco Editor | In-browser code editor for ScriptRunner scripting engine. |

## Backend

| Technology | Rationale |
| --- | --- |
| Next.js API Routes + tRPC | Type-safe API layer with end-to-end TypeScript. |
| Neon (PostgreSQL 16) | Serverless Postgres with branching. Existing account from Underpriced AI. |
| Prisma ORM | Type-safe database access, automated migrations, and schema-as-documentation. |
| Upstash Redis | Serverless Redis for caching, pub/sub, and rate limiting. Vercel-native. |
| Upstash QStash | HTTP-based message queue for background jobs, automation execution, and scheduled tasks. |
| Trigger.dev | Long-running background job execution for migrations, bulk operations, and report generation. |
| isolated-vm | Sandboxed V8 execution for ScriptRunner replacement. Note: requires Trigger.dev for execution on serverless. |
| Zod | Runtime schema validation mirroring Prisma models. Used for API input validation, env config, and form validation. |
| Pino | Structured JSON logging with redaction and correlation ID support. |

## Infrastructure & Auth

| Technology | Rationale |
| --- | --- |
| Vercel (Track A) | Next.js hosting with preview deployments, edge functions, cron jobs, and built-in CI/CD. |
| Azure Container Apps (Track B) | Managed container hosting with auto-scaling for enterprise production. |
| NextAuth.js / Auth.js | Authentication with Azure AD SAML/OIDC provider. Supports both dev and production tenants. |
| Azure AD / Entra ID | Enterprise SSO, group-based permissions, SCIM provisioning. |
| Cloudflare R2 (Track A) | S3-compatible object storage for attachments. Zero egress. |
| Azure Blob Storage (Track B) | Enterprise object storage with redundancy and compliance. |
| Ably (Track A) | Managed real-time messaging. Alternatively SSE + Upstash pub/sub. |
| Socket.io (Track B) | Native WebSocket support on Azure Container Apps. |

## External Integrations

| Integration | Implementation |
| --- | --- |
| SharePoint Online | Microsoft Graph API for page/document linking, search, embedded content. Confluence replacement. |
| GitHub | GitHub REST API + webhooks via GitHub App for PR linking, commit tracking, deployment status. |
| Salesforce | REST API + Platform Events for case-to-ticket, status sync. OAuth 2.0 Connected App. |
| Power BI | OData v4 endpoint from Ordolix; .pbit templates; row-level security via Ordolix permissions. |
| MCP Server | Model Context Protocol server (stdio + HTTP transport) for Claude Code / Claude Desktop interaction. |
| Microsoft Graph | Unified API for SharePoint, Teams notifications, Azure AD sync, calendar integration. |

# Core Data Model

The complete data model includes 40+ Prisma models organized into three categories. The full Prisma schema will be the first deliverable in Phase 1. Field-level details, indexes, and relations will be defined in the schema file itself (self-documenting via Prisma comments).

## Core Entities

| Entity | Description | Key Relationships |
| --- | --- | --- |
| Organization | Top-level tenant | Has Projects, Users, Roles |
| User | Azure AD synced user | Roles, assigned Issues, TimeLogs, Approvals |
| Project | Issue container | Workflow, IssueTypes, Permissions, Components, Versions, Boards |
| Issue | Core work item | Comments, Attachments, CustomFieldValues, History, TimeLogs, Checklists, TestLinks, GanttDependencies |
| Workflow | State machine definition | Statuses, Transitions (with Validators, Conditions, PostFunctions, ApprovalGates) |
| Status | Workflow state | Category (ToDo/InProgress/Done) |
| Transition | Directed edge between statuses | Validators, Conditions, PostFunctions, ApprovalRequirements |
| CustomField | Field definition with rollup config | Type, options, context, aggregation function |
| AutomationRule | Trigger-condition-action rule | Scoped to Project or Global, execution history |
| Board | Kanban/Scrum view | Columns, filters, swimlanes |
| Dashboard | Widget collection | DashboardWidgets with saved queries |
| Queue | Service request queue | SLA configs, assignment rules |
| AuditLog | Immutable change record | Entity, action, user, timestamp, diff |

## Add-On Feature Entities

| Entity | Description | Key Relationships |
| --- | --- | --- |
| TimeLog | Time entry on an issue | Issue, User, duration, billable flag, approval status |
| Timesheet | Aggregated time per user/period | TimeLogs, User, approval workflow |
| GanttDependency | Issue dependency for timeline | Source/target Issues, type (FS/SS/FF/SF), lag |
| SLAConfig | SLA metric definition | Queue/Project, targets, calendar, escalation rules, pause conditions |
| SLAInstance | Active SLA on an issue | Issue, SLAConfig, elapsed/remaining, breach status |
| Checklist | Checklist on an issue | Ordered ChecklistItems with assignee, due date, completion |
| Asset | CMDB configuration item | AssetType, attributes (JSONB), relationships, linked Issues |
| TestCase | Test case definition | TestSuite, steps, expected results, linked requirements |
| TestRun | Test plan execution | TestResults linking TestCases to pass/fail/skip |
| Incident | Incident record | Issues, severity, timeline, communications, status page updates |
| Approval | Approval request | Issue/Transition, approvers, status, delegation, expiry |
| FormTemplate | Dynamic form definition | Conditional fields, validation rules, issue field mappings |
| Retrospective | Sprint retro board | Categories, cards, votes, linked Issues |
| Script | Custom ScriptRunner script | Trigger type, TS/JS code, execution history |
| SavedReport | Report configuration | Dimensions, measures, chart type, schedule, recipients |

## Integration Entities

| Entity | Description | Key Relationships |
| --- | --- | --- |
| SharePointLink | Issue → SharePoint resource | Graph API resource ID, preview metadata |
| GitHubLink | Issue → GitHub resource | PR/branch/commit, state, review/merge status |
| SalesforceLink | Issue → Salesforce record | Case/Account/Contact, sync status, field mapping |
| IntegrationConfig | External service config | OAuth tokens, webhooks, field mappings, sync rules |
| MCPSession | Active MCP client session | Connected clients, permissions, audit log |

# Feature Specifications

Detailed feature specifications for all 15 native add-on replacements, 4 external integrations, and core platform features are defined in the preceding document version (v2.0) and remain unchanged. This section summarizes key architectural decisions for each feature that are relevant to Claude Code implementation.

## Feature Implementation Priority

Features are organized into three priority tiers that guide the development sequence. Tier 1 features are required for the stakeholder demo and must be visually impressive. Tier 2 features complete the platform. Tier 3 features are required for enterprise deployment.

| Tier | Features | Rationale |
| --- | --- | --- |
| Tier 1 (Demo-Critical) | Issue CRUD, Workflows, Boards, Epic Sum Up, Gantt Charts, Search (AQL), Dashboards | These are the most visually impressive and immediately comparable to Jira. Gantt charts and Epic Sum Up specifically demonstrate add-on cost elimination. |
| Tier 2 (Platform Complete) | Time Tracking, Advanced SLAs, Automation Engine, Scripting Engine, Checklists, Dynamic Forms, Approvals, Report Builder, Notifications | Complete the platform functionality. Time tracking and SLAs are critical for JSM replacement. |
| Tier 3 (Enterprise Ready) | Test Management, CMDB/Assets, Incident Management, Retrospectives, SharePoint, GitHub, Salesforce, Power BI, MCP Server, Migration Toolkit | Required for production deployment. Integrations prove the platform works within the existing ecosystem. |

## Key Architecture Decisions by Feature

- Workflow Engine: finite state machine stored as adjacency list in Postgres; transition validation runs synchronously; post-functions execute async via QStash/BullMQ

- Epic Sum Up: rollup values computed async on child issue change events; cached in Redis; pushed via real-time channel; configurable per custom field

- Gantt Charts: dependencies stored as GanttDependency records; critical path computed client-side via topological sort; drag-to-reschedule triggers bulk update API

- Time Tracking: timer state stored in Redis (user:activeTimer key); manual entries stored in TimeLog table; timesheet aggregation via Postgres materialized views refreshed by cron

- SLA Engine: SLA clock managed by background worker (QStash scheduled at 1-min intervals); pause/resume triggered by status change events; breach predictions calculated from rolling average resolution time

- Scripting Engine: on Vercel (Track A), scripts execute via Trigger.dev (which supports long-running isolated processes); on Azure (Track B), scripts run in isolated-vm within worker containers

- MCP Server: runs as a separate process/service; on Track A, deployed as a Trigger.dev background service or standalone Railway instance; on Track B, runs as a sidecar container in Azure Container Apps

- Report Builder: queries execute against Postgres using dynamically constructed SQL from dimension/measure configurations; results cached in Redis with configurable TTL

- Dynamic Forms: form definitions stored as JSON schema in FormTemplate.config (JSONB); client-side rendering via schema-driven React components; conditional logic evaluated client-side

- Test Management: TestCase steps stored as JSONB array; TestRun results are append-only for audit trail; coverage matrix computed as a Postgres view

# Development Plan

The project follows an 8-month timeline. The first 3 months focus on Tier 1 features to produce a stakeholder demo. Claude Code in agent mode is the primary development tool, with the developer (Frank) providing direction, code review, and architectural decisions.

## Phase 1: Foundation + Demo Prep (Months 1–3)

| Timeline | Deliverable | Acceptance Criteria |
| --- | --- | --- |
| Week 1 | Project scaffolding: Next.js + Prisma + tRPC + Tailwind + shadcn/ui + Vitest + Playwright. CI/CD pipeline. Claude Code skills files. | npm run dev works; CI pipeline passes; skills files reviewed |
| Week 1–2 | Prisma schema for all 40+ entities with seed data scripts | prisma migrate runs cleanly; seed creates realistic test data; schema comments on all fields |
| Week 2–3 | Azure AD SSO authentication (dev tenant) | Login via Azure AD works; roles display; session management functional |
| Week 3–5 | Issue CRUD + custom fields + Epic Sum Up rollup engine | Issues create/read/update/delete; custom field values persist; rollup computes from children to parents in real-time |
| Week 5–7 | Workflow engine with approval gates + permission system | Workflows enforce transitions; validators block invalid moves; approvals gate transitions; RBAC on all endpoints |
| Week 7–9 | Board views (Kanban + list) with real-time updates | Drag-and-drop works; real-time sync across tabs; swimlanes and filters functional |
| Week 9–11 | Gantt charts with dependencies and critical path | Timeline renders; dependencies display; drag-to-reschedule works; critical path highlights |
| Week 11–12 | Search (AQL parser) + dashboards + tooltips | AQL queries return correct results; dashboards configurable; tooltips on all features |
| Week 12 | Stakeholder demo preparation: load realistic data, polish UI, prepare cost comparison | Demo environment on Vercel with realistic data; presentation materials ready |

MILESTONE: Stakeholder demo at end of Month 3. This demo should show core issue tracking, Gantt charts, Epic Sum Up, real-time boards, and the cost comparison to secure buy-in for continued development and eventual Azure infrastructure.

## Phase 2: Platform Complete (Months 4–5)

| Timeline | Deliverable | Acceptance Criteria |
| --- | --- | --- |
| Week 13–14 | Time tracking: timers, manual entry, timesheets, approvals | Timer start/stop; timesheet grid; approval workflow; rollup to epics |
| Week 14–15 | Advanced SLAs: multi-metric, calendars, escalations, breach predictions | SLA clocks track; escalations fire; predictions alert |
| Week 15–16 | Automation engine + scripting engine | Rules execute; scripts run sandboxed; execution logs available |
| Week 16–17 | Checklists + dynamic forms + approval workflows | Checklists CRUD; forms render conditionally; approvals gate transitions |
| Week 17–18 | Report builder + notification system | Reports build and render; scheduled delivery works; notifications configurable |
| Week 18–20 | Service management: queues, request types, customer portal | Queues functional; portal renders forms; SLAs track on service requests |

## Phase 3: Integrations & Enterprise Features (Months 6–7)

| Timeline | Deliverable | Acceptance Criteria |
| --- | --- | --- |
| Week 21–22 | SharePoint integration + GitHub integration | SharePoint linking/search works; GitHub PRs auto-link to issues |
| Week 22–23 | Salesforce integration + Power BI OData endpoint | Cases create tickets; status syncs; Power BI connects and refreshes |
| Week 23–24 | MCP server + test management | Claude Code queries Ordolix via MCP; test cases/plans/runs functional |
| Week 24–25 | CMDB/assets + incident management + retrospectives | Assets CRUD; incidents create from issues; retro action items create issues |
| Week 25–28 | Migration toolkit: Jira + all add-on data export, transform, import | Dry run migration with full data integrity validation |

## Phase 4: Launch (Month 8)

| Timeline | Deliverable | Acceptance Criteria |
| --- | --- | --- |
| Week 29–30 | Internal beta with pilot teams | 3+ teams actively using Ordolix daily |
| Week 30–31 | Bug fixes, performance optimization, UX polish | All critical bugs resolved; performance budgets met |
| Week 31–32 | Final migration, cutover, documentation, training | All projects migrated; Jira decommissioned; user guides published |

# Demo Strategy for Stakeholder Buy-In

## Demo Environment

- Hosted on Vercel at a preview URL (e.g., Ordolix-demo.vercel.app)

- Populated with realistic (but non-sensitive) data migrated from a Jira project export

- Azure AD SSO working so stakeholders can log in with their own Microsoft accounts

- All Tier 1 features functional: issue tracking, boards, Gantt charts, Epic Sum Up, search, dashboards

## Demo Narrative

- Open with the cost slide: current annual Ordolixsian spend (Jira + Confluence + all add-ons) vs. Ordolix running on $25/month of infrastructure

- Show the board view side-by-side with Jira — demonstrate feature parity with cleaner UI

- Demonstrate Gantt charts with dependency management — "this replaces BigPicture at $X/year"

- Show Epic Sum Up rollup — "this replaces the Epic Sum Up plugin at $X/year"

- Show the AQL search — "same power as JQL, cleaner syntax"

- Demo real-time collaboration — open on two devices, show live board updates

- Show the MCP integration — have Claude Code create an issue and query the board via natural language

- Close with the roadmap: Phase 2 add-ons, Phase 3 integrations, Phase 4 migration and cutover

## Buy-In Success Criteria

- Leadership approval to allocate dedicated development time (not nights-and-weekends)

- Budget approval for Azure infrastructure (Track B transition)

- Identification of 3+ pilot teams willing to use Ordolix for daily work during beta

- IT Security review initiated for production deployment compliance

# Risks and Mitigations

| Risk | Severity | Mitigation | Owner |
| --- | --- | --- | --- |
| Expanded scope exceeds 8 months | High | Tier-based prioritization; Tier 1 delivers demo in 3 months; lower tiers shift to v1.1 if needed | Project Lead |
| Single developer dependency | High | Self-documenting code, Claude Code skills, comprehensive tests, modular architecture | Project Lead |
| Vercel serverless limitations (WebSocket, long jobs) | Medium | Ably for real-time, Trigger.dev for long jobs; abstraction layer enables Track B swap | Project Lead |
| Scripting engine security | High | isolated-vm sandboxing via Trigger.dev; resource limits; no filesystem/network access; code review | Project Lead + Security |
| Migration data integrity | High | Automated validation suite; multiple dry runs; parallel operation; add-on data validation | Project Lead |
| Stakeholder demo fails to secure buy-in | Medium | Focus Tier 1 on most visually impressive features; prepare detailed cost comparison; demo to multiple audiences | Project Lead |
| Neon/Vercel free tier limits exceeded | Low | Monitor usage; Pro tier on both already active; costs remain minimal | Project Lead |
| Salesforce API rate limits | Medium | Request batching, caching, Platform Events for real-time sync | Project Lead |
| MCP protocol evolution | Low | Follow spec closely; abstract transport layer; monitor Anthropic releases | Project Lead |

# Cost Analysis

## Cost Comparison

| Category | Current Annual Cost | Ordolix (Track A) | Ordolix (Track B) |
| --- | --- | --- | --- |
| Jira Cloud licensing | [Current cost] | $0 | $0 |
| Confluence Cloud licensing | [Current cost] | $0 (SharePoint) | $0 (SharePoint) |
| Tempo Timesheets | [Current cost] | $0 (native) | $0 (native) |
| ScriptRunner | [Current cost] | $0 (native) | $0 (native) |
| BigPicture / Adv. Roadmaps | [Current cost] | $0 (native) | $0 (native) |
| eazyBI | [Current cost] | $0 (native) | $0 (native) |
| Insight / Assets | [Current cost] | $0 (native) | $0 (native) |
| ProForma | [Current cost] | $0 (native) | $0 (native) |
| Epic Sum Up | [Current cost] | $0 (native) | $0 (native) |
| Checklist add-ons | [Current cost] | $0 (native) | $0 (native) |
| TestRail | [Current cost] | $0 (native) | $0 (native) |
| Other add-ons | [Current cost] | $0 (native) | $0 (native) |
| Infrastructure | Included in licenses | $20–40/mo | [Azure costs] |
| AI tooling (Claude) | N/A | [Claude subscription] | [Claude subscription] |
| TOTAL | [Sum all current] | ~$500–800/year | [Azure estimate] |

# Immediate Next Steps

- Initialize GitHub repository with Next.js 15, TypeScript strict, Prisma, tRPC, Tailwind, shadcn/ui, Vitest, Playwright

- Create CLAUDE.md and all Claude Code skills files in the repository

- Configure Vercel project linked to GitHub repo with preview deployments

- Set up Neon database with development branch and configure Prisma

- Set up Upstash Redis and QStash accounts with Vercel integration

- Register Azure AD developer tenant via M365 Developer Program for SSO development

- Create GitHub Actions CI/CD workflow with all quality gates

- Begin Phase 1 development: Prisma schema (40+ models) as first Claude Code agent task

- Run Jira usage audit: extract all configurations, add-on data, and Confluence cross-references

- Compile complete cost inventory of all current licenses for ROI presentation

- Register GitHub App for GitHub integration webhook development

- Verify Microsoft Graph API permissions needed for SharePoint integration

# Appendices

## Appendix A: Add-On Feature Mapping & Cost Elimination

Populate with actual Proofpoint license costs for ROI analysis.

| Add-On | Annual Cost | Ordolix Replacement | Feature Parity |
| --- | --- | --- | --- |
| Tempo Timesheets | [cost] | Native Time Tracking | Full + budget tracking |
| ScriptRunner | [cost] | Native Scripting Engine | Full; Groovy → TypeScript |
| BigPicture / Adv. Roadmaps | [cost] | Native Gantt Charts | Full + critical path |
| eazyBI | [cost] | Native Report Builder + Power BI | Core native; Power BI for advanced |
| Insight / Assets | [cost] | Native CMDB | Full + Azure AD device sync |
| ProForma | [cost] | Native Dynamic Forms | Full + multi-page |
| Epic Sum Up | [cost] | Native Field Rollup | Full + custom aggregations |
| Checklist for Jira | [cost] | Native Checklists | Full + workflow integration |
| TestRail (separate) | [cost] | Native Test Management | Full + issue integration |
| JSM Premium (approvals/SLA) | [cost] | Native Approvals + SLAs | Full + breach predictions |
| Confluence | [cost] | SharePoint Integration | Feature parity via Graph API |
| TOTAL ELIMINATED | [sum] |  |  |

## Appendix B: AQL Specification

- project = "ORDOLIX" AND status = "In Progress" AND assignee = currentUser()

- priority IN ("High", "Critical") AND created >= -7d

- type = "Bug" AND resolution IS EMPTY ORDER BY priority DESC

- timeLogged > 8h AND sprint = currentSprint()

- slaBreached = true AND queue = "IT Support"

- asset.type = "Server" AND asset.status = "Production"

- testCoverage < 80% AND labels CONTAINS "release-candidate"

- ganttDependency.type = "finish-to-start" AND dueDate <= +7d

## Appendix C: Integration API Reference

| Integration | API / Protocol | Auth | Key Endpoints |
| --- | --- | --- | --- |
| SharePoint | Graph API v1.0 | OAuth 2.0 (Azure AD) | Sites, Pages, Search, DriveItems |
| GitHub | REST API v3 + Webhooks | GitHub App (JWT) | PRs, Commits, Branches, Deployments |
| Salesforce | REST API + Platform Events | OAuth 2.0 JWT Bearer | Cases, Accounts, Contacts |
| Power BI | OData v4 (Ordolix-hosted) | API token / Azure AD SP | Issues, Projects, Metrics |
| MCP | MCP (stdio + HTTP) | API token | Resources + Tools |

## Appendix D: SharePoint-Confluence Migration Mapping

| Jira-Confluence Feature | Ordolix-SharePoint Equivalent | Implementation |
| --- | --- | --- |
| Page links on issues | SharePoint links on issues | Graph API; SharePointLink entity |
| Jira macro in Confluence | Ordolix web part in SharePoint | SPFx web part via REST API |
| Create page from Jira | Create page from Ordolix | Graph API page creation |
| Filter results in Confluence | Ordolix data in SharePoint | Power BI embedded in SharePoint |
| Search from Jira | Search from Ordolix | Graph API search |
| Space per project | Site per project | Configurable association |

## Appendix E: Claude Code Context Files

These files live in the repository root and are loaded by Claude Code for session context:

- CLAUDE.md — Primary context: architecture, conventions, tech stack, directory structure, this document summary

- CLAUDE_WORKFLOW.md — Workflow engine: state machine, validators, approval gates, post-functions

- CLAUDE_AUTOMATION.md — Automation + scripting: triggers, conditions, actions, sandboxed execution

- CLAUDE_MIGRATION.md — Migration toolkit: Jira API, add-on data formats, transformation rules

- CLAUDE_SCHEMA.md — Database schema: all 40+ entities, relationships, indexes, rollup patterns

- CLAUDE_INTEGRATIONS.md — External integrations: Graph API, GitHub API, Salesforce API, OData, MCP

- CLAUDE_SHAREPOINT.md — SharePoint-Confluence migration: parity matrix, Graph API patterns

- CLAUDE_ADDONS.md — Add-on features: Gantt algorithms, SLA logic, time tracking, test management

- CLAUDE_MCP.md — MCP server: resource definitions, tool specs, transport config, permissions

- CLAUDE_TESTING.md — Testing strategy: TDD workflow, factory patterns, mock setup, coverage requirements

- CLAUDE_HOSTING.md — Hosting architecture: Track A (Vercel/Neon) vs Track B (Azure), provider interfaces, migration path